## Product Backlog
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Create applicant profile | As a TA, I want to create an applicant profile, so that I can apply for teaching assistant jobs. | High | 1 | 1. TA can enter personal details including name, student ID, email, and skills. 2. Required fields must be validated before saving. 3. The system must save the profile in a text-based file format. 4. TA can reopen and edit the saved profile later. | 5 | Foundation for application features. | 2026-03-18 | 2026-03-25
US02 | Upload CV | As a TA, I want to upload my CV, so that MO and the admin can reciew. | High | 1 | 1. As can upload resume files from local storage. 2. The system only accepts file types supported and defined by the team. 3. Uploaded resumes will be stored and accessible to MO and Admin. 4. TAs may replace old resumes with new versions before the application deadline. | 3 | Depends on applicant profile; Core basic functions / Core foundational features. | 2026-03-17 | 2026-03-23
US03 | Browse available jobs | As a TA, I want to browse available jobs, so that I can find suitable opportunities. | High | 1 | 1. TA can upload resume files from local storage. 2. The system only accepts file types supported and defined by the team. 3. Uploaded resumes will be stored and accessible to MO and Admin. 4. TAs may replace old resumes with new versions before the application deadline. | 5 | Core browsing function. | 2026-03-21 | 2026-03-25
US04 | Search and filter jobs | As a TA, I want to search and filter jobs, so that I can find relevant roles more efficiently. | Medium | 3 | 1. TAs can search by keywords such as module name and working hours. 2. The filtered results will be updated correctly according to the selected criteria. 3. The complete list of open positions will be restored after clearing the filter criteria. | 3 | Depends on job list display. | 2026-04-17 | 2026-04-21
US05 | Apply for a job | As a TA, I want to apply for a job and indicate whether I am willing to accept reassignment, so that I can be considered for the role and suitable alternative vacancies if needed. | High | 1 | 1. TA can apply only to currently open jobs. 2. The application allows TA to choose whether they are willing to accept reassignment. 3. The system prevents application if the profile is incomplete and stores the application with timestamp, applicant details. 4. After submission, the application status is shown as Submitted. | 3 | Depends on applicant profile and job list. | 2026-03-18 | 2026-03-23
US06 | View application history | As a TA, I want to view my application history, so that I can track all my submissions. | Medium | 2 | 1. TA can view all jobs they have applied for. 2. Each application shows job title, submission date and current status. 3. Applications are sorted by most recent first. 4. TA can open an application to view details. | 2 | Depends on job application records. | 2026-04-05 | 2026-04-09
US07 | Check application status | As a TA, I want to check my application status, so that I know whether I was accepted, rejected or waiting for reassignment. | High | 1 | 1. The system shows the current status for each submitted application. 2. If TA chose not to accept reassignment, the possible statuses are Submitted, Accepted and Rejected. 3. If TA chose to accept reassignment, the possible statuses are Submitted, Accepted, Waiting for Reassignment and Rejected. 4. Displayed status must match the latest stored record and updates made by Admin or MO are visible to TA. | 2 | Depends on MO review and update flow. | 2026-03-21 | 2026-03-24
US08 | Post a job | As a MO, I want to post a job, so that students can apply for TA positions. | High | 1 | 1. MO can create a job with title, description, required skills workload and number of TAs. 2. Required fields must be validated before posting. 3. Posted jobs appear in the list of available jobs. 4. Each job is stored in a text-based file format. | 3 | Core employer-side function. | 2026-03-22 | 2026-03-25
US09 | Edit or close a job | As a MO, I want to edit or close a job, so that outdated or filled positions are no longer available. | Medium | 2 | 1. MO can edit job details before the deadline. 2. MO can manually close a job. 3. Closed jobs cannot receive new applications. 4. The job list clearly distinguishes open and closed jobs. | 3 | Depends on job posting. | 2026-04-06 | 2026-04-09
US10 | Review applicants | As a MO, I want to review applicants and the CVs, so that I can compare and select suitable candidates. | High | 2 | 1. MO can view all applicants for a selected job. 2. Applicant information includes profile summary and the CV. 3. MO can open an applicant record to view full details. 4. The system shows applicants only for the selected job. | 3 | Depends on job application records and admin forwarding. | 2026-04-07 | 2026-04-11
US11 | Update applicant status | As a MO, I want to update an applicant's status, so that the recruitment process can move forward. | High | 2 | 1.MO can change an application status to Accepted or Rejected. 2.The updated status is stored immediately in the data file. 3.TA can see the new status in their application view. 4.Accepted and rejected applicants are clearly identified in the system. | 3 | Depends on applicant review. | 2026-04-05 | 2026-04-08
US12 | Validate missing or invalid input | As a MO or TA, I want the system to validate missing or invalid input, so that incorrect data is not saved. | High | 1 | 1. Required form fields are checked before submission. 2. Invalid input triggers a clear error message. 3. Invalid data is not saved. 4. MO or TA can correct input and resubmit successfully. | 3 | Cross-cutting requirement for all forms. | 2026-03-18 | 2026-03-23
US13 | Role-based access | As a user, I want role-based access, so that I can only access functions relevant to my role. | High | 3 | 1.The system shows correct menu options for each role. | 3 | Important for clean scope and security. | 2026-04-13 | 2026-04-16
US14 | Position matching recommendation | As an admin, I want the system to suggest matching applicants based on skills, so that I can shortlist candidates faster. | Low | 4 | 1. The system compares job requirements with CV data. 2. Each applicant receives a visible matching result or score. 3. The recommendation includes an explainable reason. | 8 | AI-assisted enhancement; not part of MVP. | 2026-05-03 | 2026-05-18
US15 | View recruitment overview | As an Admin, I want to view complete recruitment information, so that I can monitor course details, application progress and applicant materials in one place. | Medium | 3 | 1. Admin can view course description, requirements and current recruitment status for each course. 2. Admin can view the application status and applicant list for each course. 3. Admin can open an applicant record to view applicant information and submitted materials. | 2 | Supports admin monitoring of overall recruitment flow. | 2026-04-14 | 2026-04-18
US16 | Reassign rejected applicants | As an Admin, I want to reassign rejected applicants to courses with unfilled positions after the deadline, so that vacancies can be filled more efficiently. | Medium | 3 | 1. After the application deadline, Admin can view applicants who are eligible for reassignment. 2. Admin can reassign an applicant only to a course that still has unfilled positions. 3. The system records the reassignment and updates the application to the appropriate reassignment status. 4. The reassignment result is visible in both the admin view and the TA application status view. | 3 | Depends on applicant status management and vacancy tracking. | 2026-04-18 | 2026-04-25
US17 | Issue final rejection | As an Admin, I want to issue a final rejection after the deadline, so that recruitment decisions can be finalized for applicants who will not be reassigned. | Medium | 3 | 1. After the deadline, Admin can mark an applicant as rejected. 2. A finally rejected applicant cannot be reassigned to another course. 3. The final rejection is stored immediately and visible to the TA. 4. The system keeps a clear record of the final decision. | 2 | Supports post-deadline recruitment decisions. | 2026-04-25 | 2026-04-27
US18 | Close course recruitment | As an Admin, I want to close recruitment for a course, so that no further applications or reassignment can be made once hiring is complete. | Medium | 3 | 1. Admin can manually close recruitment for a course. 2. Closed courses are clearly marked in the system. 3. Closed courses cannot accept new applications. 4. Existing recruitment records remain visible after closure. | 2 | Supports course-level recruitment control. | 2026-04-06 | 2026-04-11